## Sheet1
Item Number | Goal | Task | Estimated Time | Assigned To | Target Deadline | Actual Time | Actual Delivery | Status | Comments
1 | GUI for Evolution 1
1.12 |  | Display the graphical map with territory name and adjacency information. | 3h | Gean | 2023-04-06 | 5h | 2023-04-07 | Completed
1.13 |  | Display colored territories to disclose owner information. | 2h | Gean |  | 3h |  | Completed
1.14 |  | Inform the player of his/her color. | 1h | Gean |  | 2h |  | Completed
1.15 |  | Display the number of units inside each territory. | 1h | Gean |  | 2h |  | Completed
1.16 |  | Display a message box used to inform the player game status. | 1h | Gean |  | 2h |  | Completed
1.17 |  | Display three buttons (Move/Attack/Submit) | 1h | Gean |  | 2h |  | Completed
1.18 |  | Allow the player to choose the order by clicking one of the three buttons. | 2h | Gean |  | 3h |  | Completed
1.19 |  | If the player chooses Move or Attack, allow him/her to choose the territory by clicking. | 2h | Gean |  | 4h |  | Completed
1.2 |  | Display a message box used to take inputs (e.g., the number of units) from the player. | 3h | Gean |  | 4h |  | Completed
1.21 |  | If the player chooses Submit, send all orders to the server. | 3h | Gean |  | 4h |  | Completed
1.22 |  | Display a message box used to inform the player of the input validity. | 2h | Gean |  | 3h |  | Completed
1.23 |  | Display the winning information if there is a winner, otherwise display the next round information. | 1h | Gean |  | 2h |  | Completed
2 | Food Resource & Units
2.11 |  | Each territory has a distance to all adjacent territories. | 1h | Yifan | 2023-04-04 | 1h | 2023-04-02 | Completed
2.12 |  | Each player is initialized with food units. | 0.5h | Yifan |  | 0.5h | 2023-04-02 | Completed
2.13 |  | Some territories should have food resource that produces food units for their owner at a certain rate. | 0.5h | Yifan |  | 0.5h | 2023-04-02 | Completed
2.14 |  | Each move order consumes food units based on a given formula. | 1h | Yifan |  | 1h | 2023-04-02 | Completed
2.15 |  | The game must pick the minimum total cost valid path when determining the cost. | 2.5h | Yifan |  | 1h | 2023-04-02 | Completed
2.16 |  | Each attack order consumes food units based on a given formula. | 2h | Yifan |  | 1h | 2023-04-02 | Completed
2.17 |  | The server should prompt the player to re-enter the order if the food units of that player are insufficient. | 1h | Yifan |  | 1h | 2023-04-02 | Completed
2.18 |  | The server should execute the move/attack order with corresponding food units deducted for each player. | 2h | Yifan |  | 1h | 2023-04-02 | Completed
2.19 |  | The player shall also increase their resource totals by adding the resource production of each territory that they own at the end of the turn. | 1h | Yifan |  | 1h | 2023-04-02 | Completed
3 | Technology Resource & Units
3.11 |  | Each player is initialized with technology units. | 1h | Mac | 2023-04-04 | 1h | 2023-04-04 | Completed
3.12 |  | Some territories should have technology resource that produces technology units for their owner at a certain rate. | 2h | Mac |  | 1h | 2023-04-04 | Completed
3.13 |  | The server needs to perform the upgrade order if the order is valid. | 1h | Mac |  | 2h | 2023-04-04 | Completed
3.14 |  | The player shall also increase their TECH resource totals by adding the resource production of each territory that they own at the end of the turn. | 1h | Mac |  | 1h | 2023-04-04 | Completed
3.15 |  | Update the combat rules based on the sum of the bonus. | 3h | Mac |  | 8h | 2023-04-05 | Completed
3.16 |  | At the end of each turn, one new basic unit shall appear in each territory. | 1h | Mac |  | 1h | 2023-04-04 | Completed
4 | Unit Tech Level in Move/Attack
4.11 |  | Each move order needs to specify the unit tech level. | 2h | Yifan | 2023-04-08 | 3h | 2023-04-09 | Completed
4.12 |  | The server needs to validate the move order based on the tech level. | 1h | Yifan |  | 3h | 2023-04-09 | Completed
4.13 |  | The server needs to execute the move order based on the tech level. | 1h | Yifan |  | 1h | 2023-04-09 | Completed
4.14 |  | Each attack order needs to specify the unit tech level. | 2h | Yifan |  | 3h | 2023-04-09 | Completed
4.15 |  | The server needs to validate the attack order based on the tech level. | 1h | Yifan |  | 3h | 2023-04-09 | Completed
4.16 |  | The server needs to execute the attack order based on the tech level. | 1h | Yifan |  | 1h | 2023-04-09 | Completed
5 | Refactor Upgrade Action
5.1 |  | The player can issue an upgrade order (territory, units to be upgraded, desired unit level) | 2h | Mac | 2023-04-08 | 4h | 2023-04-09 | Completed
5.2 |  | The server needs to validate the upgrade order and send back a validation message to the client. | 3h | Mac |  | 4h | 2023-04-09 | Completed
6 | GUI Display New Features
6.1 |  | Display food resources and technology resources for each territory | 2h | Gean | 2023-04-10 | 3h | 2023-04-11 | Completed
6.2 |  | Display the distance to each adjacent territory. | 2h | Gean |  | 3h | 2023-04-11 | Completed
6.3 |  | Display the button for Upgrade. | 2h | Gean |  | 3h | 2023-04-11 | Completed
6.4 |  | Allow the player to choose the Upgrade by clicking on the button. | 3h | Gean |  | 4h | 2023-04-11 | Completed
6.5 |  | If the player chooses Upgrade, allow him/her to choose the territory by clicking. | 2h | Gean |  | 3h | 2023-04-11 | Completed
6.6 |  | Display a message box used to take inputs (e.g., the number of units, tech level) from the player. | 2h | Gean |  | 3h | 2023-04-11 | Completed
7 | Fine Tune Parameters
7.1 |  | Fine tune the initialization of food and technology units for each player. | 1h | Mac | 2023-04-10 | 2h | 2023-04-11 | Completed
7.2 |  | Fine tune the food and technology production rate for each territory. | 1h | Mac |  | 2h | 2023-04-11 | Completed
7.3 |  | Fine tune the distance between territories. | 1h | Mac |  | 2h | 2023-04-11 | Completed
8 | Refactor
|  | Code refactor. | N/A | Everyone | 2023-04-11 | N/A | 2023-04-12 | Completed

## Statuses
Unassigned
Assigned
Started
Testing
Code Review
Completed